## Overview
Hospital Preparedness Program (HPP) Health Care Coalition (HCC) Readiness Plan Template Overview
Purpose | You may use this readiness plan template to document how you will carry out activities and meet requirements for upcoming projects and acitivities throughout the course of the 5-year budget period (BP). The Office of Health Care Readiness (OHCR) is providing this work plan and budget template as an optional resource.
Notice of Funding Opportunity (NOFO) Instructions | You must submit a detailed fiscal year (FY) 2024 readiness plan in the first BP. Priorities: In this readiness plan, your HCC must describe top strategic priorities of your HCC(s) for each BP. Your HCC(s) should collaborate with you as they develop their top strategic priorities so that their Readiness Plan and the Strategic Plan for FY 2024–2028 are aligned and can support one another. Your HCC(s) may update their priorities each BP based on the previous assessments. Implementation Planning: Describe how your HCC(s) will implement activities. This should include your HCC(s)’s method for: • Developing the required materials identified in this NOFO, including approach, timelines, and expected milestones. Note: You and your HCC(s) must adhere to the submission deadlines specified in the timing and deadlines table. • Addressing gaps identified through assessments. Note: This section can be updated on a rolling basis as you and your HCC(s) complete assessments and identify areas for improvement. • Engaging community partners. • Facilitating continuous improvement from the previous BP. HCC Growth and Development: Describe how your HCC(s) will develop as an organization, including how your HCC(s) will: • Manage and improve administrative and financial functions. • Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).
Readiness Plan Template Content
Tab | Description
Activity Requirements | A reference table of activity requirements for the FY 2024–2028 HPP NOFO with submission instructions and timeline and administrative oversight activities.
HCC Priorities | Readiness Plan component
HCC Development | Readiness Plan component
Establish Governance | Readiness Plan component
Assess Readiness | Readiness Plan component
Plan and Implement | Readiness Plan component
Exercise and Improve | Readiness Plan component
Training and Exercise (T&E) Plan Instructions | T&E Plan component
T&E Plan | T&E Plan component
Reference Table
HPP NOFO Outcomes | Description
Establish and act on multi-year priorities. | Outcomes include: • Health care delivery system readiness to respond to a shifting threat landscape and community needs over multiple years. • Continuous programmatic and administrative improvement on multi-year priorities.
Enhance and sustain HCCs. | Outcomes include: • HCC governance, management, and operations that reflect community partnerships.
Coordination. | Outcomes include: • Coordinated planning and decision-making among health care delivery system partners. • State, local, tribal, and territorial agencies, HCCs, and other partners provide integrated health care response incident management (Emergency Support Function #8 [ESF-8] – Public Health and Medical Services).
Continuity of health care service delivery. | Outcomes include: • A resilient health care workforce able to safely meet response and recovery demands. • Suficient space, systems, staff, and resources to support patient movement and patient care delivery during response and recovery. Note: As used in the HPP NOFO, “health care workforce” does not refer only to clinical providers, but also includes all those who support the functioning of health care during disasters and emergencies.
HPP NOFO Core Functions | Description
Assessment and risk mitigation. | Anticipate challenges and mitigate risks to support decision-making that meets community or jurisdiction health care needs during a disaster or emergency.
Information sharing. | Collect and share near real-time information to provide multidirectional health care situational awareness during an emergency or disaster.
Specialty care planning and coordination. | Incorporate necessary expertise to support health care readiness planning, disaster and incident management, including for specialty care delivery, and/or to address specific hazards or events.
Respond. | Coordinate and support the implementation of plans, policies, and procedures among recipients, HCCs, HCC members, and their partners to address patient care needs during an emergency or disaster.
Health care workforce support. | Equip, protect, and support the health care workforce by providing access to health care readiness resources, training, and exercises.
Resource management. | Facilitate resource management and planning among recipients, HCCs, HCC members, and their partners to mitigate shortfalls, maintain operations, and sustain delivery of patient care services during an emergency or disaster.
Training, exercise, and evaluation. | Conduct trainings, exercises, and evaluations that incorporate input from assessments, plans, policies, and previous trainings and exercises to evaluate, validate, and improve readiness and response processes.
Continuity and recovery. | Support the improvement of processes and systems that promote continuity of health care operations and aid in recovery.
Organizational development. | Create and carry out strategies to sustain and grow HCCs and their partnerships.
End of worksheet

## Activity Requirements
FY 2024–2028 HPP NOFO Requirements
The following table is for your reference. Please refer to the HPP NOFO Timing and Deadlines table for activities 1-4 on p. 44-45 of the HPP NOFO. Refer to the Benchmarks table for Recipient and HCC benchmarks on p. 42 of the HPP NOFO.
Activities | Guidance
0. Administrative Oversight Activities | 0. Administrative Oversight – Guidance
0.1 Program Administration | Work with HCCs and pertinent partners to maintain program oversight throughout the period of performance. Please adhere to program requirements listed in the NOFO and the rules listed in 45 Code of Federal Regulations (CFR) Part 75.
0.2 Financial Administration | Develop and administer budgets that support submitted work plans and comply with the rules listed in 45 CFR Part 75, Uniform Administrative Requirements, Cost Principles, and Audit Requirements for U.S. Department of Health and Human Services (HHS) Awards throughout the period of performance.
Activities | Submission Instructions and Timeline | Responsible Owner
1. Establish Governance Activities | 1. Establish Governance – Submission Instructions and Timeline | 1. Establish Governance – Responsible Owner
1.1 HCC Governance Document | Submit by January 31, 2025 (BP1). Review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
1.2 Jurisdiction Information | Submit by January 31, 2025 (BP1). Review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
2. Assess Readiness Activities | 2. Assess Readiness – Submission Instructions and Timeline | 2. Assess Readiness – Responsible Owner
2.1 Risk Assessment (RA) Note: Previously known as Jurisdiction Risk Assessment (JRA) | Submit once every five years. If you submitted a JRA during the prior HPP FY 2019–2023 period of performance, you must submit the RA five years after that submission. | HPP recipient with input from HCCs
2.2 Hazard Vulnerability Assessment (HVA) | Submit by January 31, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
2.3 Readiness Assessment | Submit by January 31, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
2.4 Supply Chain Integrity Assessment | Review the current Supply Chain Integrity Assessment and submit updated material each BP. If you and your HCC(s) do not have a supply chain assessment, submit this by December 31, 2026 (BP3). Review and submit updated material each BP from BP4–BP5. | HCC in coordination with HPP recipient
2.5 Workforce Assessment | Submit by December 31, 2026 (BP3). Review each BP from BP4–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
2.6 Cybersecurity Assessment | Due by June 30, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
2.7 Extended Downtime Health Care Delivery Impact Assessment | Due by June 30, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
3. Plan and Implement Activities | 3. Plan and Implement – Submission Instructions and Timeline | 3. Plan and Implement – Responsible Owner
3.1 Strategic Plan for FY 2024–2028 | Due by March 31, 2025 (BP1). Review each BP from BP2–BP5 and submit updated material as needed. | HPP recipient with input from HCCs
3.2 Readiness Plan | Due by March 31, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
3.2.1 Training and Exercise Plan | Due by March 31, 2025 (BP1). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
3.3 Response Plan Activities | 3.3 Response Plan – Submission Instructions and Timeline | 3.3 Response Plan – Responsible Owner
3.3.1 Information-Sharing Plan | Review the current information-sharing plan each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have an information-sharing plan, submit this by June 30, 2025 (BP1). Review each BP from BP2–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.2 Resource Management Plan | Review the current resource management plan each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have a resource management plan, submit this by June 30, 2025 (BP1). Review each BP from BP2–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.3 Workforce Readiness/Resilience Plan | Due by December 31, 2026 (BP3). Review each BP from BP4–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.4 Medical Surge Support Plan | Review the current medical surge support plan each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have a medical surge support plan, submit by June 30, 2025 (BP1). Review each BP from BP2–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.5 Patient Movement Plan | You and your HCC(s) must define the submission deadline for the Patient Movement Plan when you and your HCC(s) develop your Readiness Plan. Once submitted, review each BP and submit updated material as needed. | HPP recipient with input from HCCs
3.3.6 Allocation of Scarce Resources Plan | You and your HCC(s) must define the submission deadline for the Allocation of Scarce Resources Plan when you develop your Readiness Plan. Once submitted, review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
3.4 Continuity and Recovery Plan Activities | 3.4 Continuity and Recovery Plan – Submission Instructions and Timeline | 3.4 Continuity and Recovery Plan – Responsible Owner
3.4.1 Continuity of Operations Plan (COOP) | Review the current COOP each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have a COOP, complete this by June 30, 2025 (BP1). Once submitted, review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
3.4.2 Cybersecurity Support Plan | Due by June 30, 2026 (BP2). Review each BP from BP3–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.4.3 Extended Downtime Support Plan | Due by June 30, 2026 (BP2). Review each BP from BP3–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.4.4 Recovery Plan | Due by June 30, 2026 (BP2). Review each BP from BP3–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
4. Exercise and Improve Activities [1] | 4. Exercise and Improve – Submission Instructions and Timeline | 4. Exercise and Improve – Responsible Owner
4.1 Medical Response and Surge Exercise (MRSE) | Complete the exercise and submit the MRSE Exercise Reporting Tool by June 30 of each BP. | HCC with HPP recipient support
4.2 Patient Movement Exercise | Complete once, within one year of submitting the Patient Movement Plan. | HPP recipient with HCC participation
4.3 Federal Patient Movement Exercise | If applicable, complete once every three years, or as required by other cooperative agreements/programs. | HCC with HPP recipient support
4.4 Cybersecurity Exercise | Complete once by June 30, 2027 (BP3). | HCC with HPP recipient support
4.5 Non-Cyber Extended Downtime Exercise | Complete once between BP3–BP5. | HCC with HPP recipient support
4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Complete once in the five-year period of performance. | HPP recipient with HCC participation
4.7 Statewide Exercise | Complete once in the five-year period of performance. | HPP recipient with HCC participation
[1] Please refer to Exercise and Improve section of the HPP NOFO for a full list of requirements for this section.
Please note that certain compliance requirements, like the requirement to conduct at least one exercise that address the needs of at-risk individuals and communities most impacted by disasters, are not listed in this table.
End of Worksheet
X1A0T

## Readiness Plan Overview (hidden)
Readiness Plan Overview
HCC Priorities | On the priorities tab, describe top strategic priorities of your HCC(s) for each BP. HCCs should collaborate with the recipient as they develop their top strategic priorities so that your Readiness Plan shows alignment to the Strategic Plan for FY 2024-2028 and can support one another. Your HCC(s) may update their priorities each BP based on the previous assessments.
Implementation Planning | On the activity tabs, develop the required materials identified in the NOFO, including approach, timelines, and expected milestones. • adhere to the submission deadlines specified in the activity requirements tab •
• Use your readiness assessment Addressing gaps identified through assessments. Note: This section can be updated on a rolling basis as you and your HCC(s) complete assessments and identify areas for improvement.
• Engaging community partners.
• Facilitating continuous improvement from the previous BP.
HCC Development
Describe how your HCC(s) will develop as an organization, including how your HCC(s) will: • (HCC) Manage and improve administrative and financial functions. • (HCC) Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).
• (HCC) Manage and improve administrative and financial functions.
• (HCC) Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).

## HCC Priorities
Readiness Plan – Priorities
Description | On the priorities tab, describe top strategic priorities of your HCC(s) for each BP. HCCs should collaborate with the recipient as they develop their top strategic priorities so that your Readiness Plan shows alignment to the Strategic Plan for FY 2024–2028 and can support one another. Your HCC(s) may update their priorities each BP based on the previous assessments.
Priority | HCC Priorities | Description and Approach
Rank of Priority | Select your priority area from highest priority to lowest (minimum 5). | Describe your approach to address your priority needs including: 1. Primary reason(s) for priority (e.g., critical gap finding, strategic plan alignment, etc.) 2. Briefly summarize how the HCC will approach the priority (e.g., The HCC will complete the patient movement plan in year 1 and perform a detailed gap analysis regarding needs in the region).
Example | 1. Establish governance | 1. Our HCC has determined that financial and independent growth is the best way to develop a sustainable coalition. 2. In year one, the HCC will contract with financial and marketing specialists to determine a path forward to 501c3 incorporation and income sustainability.
1 | 0.2 Financial Administration | Goal: Ensure Sustainability: 1. Develop and implement a Coalition sustainability plan. 2. In year one, assess and prioritize coalition activities in loss of or reduction of federal funding. 3. Identify alternate funding sources
2 | 2.3 Readiness Assessment | Goal: Build and Sustain Capabilities: 1. Assess, identify and prepare for gaps in readiness. 2. In year one, complete readiness assessment and readiness plan.
3 | 1.2 Jurisdiction Information | Goal: Increase Membership and Engagement: 1. Identify and engage community leaders. 2. In year one, work with county emergency management and health department leaders to identify community leaders. 3. Engage EMS. 4. In year 1, work with Regional Trauma Advisory Board to plan for an EMS Symposium.
4 | 3.3.4 Medical Surge Support Plan | Goal: Ensure all counties have family reunification/family assistance center plans. 1. Assess status of county plans. 2. In year one, develop an FRC/FAC toolkit, promote implementation of Pulsara, offer counties FRC tabletop; and enhance regional FAC response team capabilities.
5 | 3.3.4 Medical Surge Support Plan | Goal: Close HVA gaps re evacuation equipment. 1. In year one, place third and final evacuation cache in north end of region.
6 | 3.3.5 Patient Movement Plan | Goal: A statewide patient movement plan and exercise. 1. In year one, work with the Florida Committee on Trauma and the Regional Trauma Preparedness Committee to draft a pilot plan.
7 | 3.3.1 Information-Sharing Plan | Goal: Increase the use of EMResource across the region. 1. In year one, identify and educate counties not using EMResource daily.
8 | Select One | [insert Description and Approach]
9 | Select One | [insert Description and Approach]
10 | Select One | [insert Description and Approach]
End of Worksheet
Select One
0. Administrative Oversight
0.1 Program Administration
0.2 Financial Administration
1. Establish governance
1.1 HCC Governance Document
1.2 Jurisdiction Information
2. Assess readiness
2.1 Risk Assessment (RA)
2.2 Hazard Vulnerability Assessment (HVA)
2.3 Readiness Assessment
2.4 Supply Chain Integrity Assessment
2.5 Workforce Assessment
2.6 Cybersecurity Assessment
2.7 Extended Downtime Health Care Delivery Impact Assessment
3. Plan and implement
3.1 Strategic Plan for FY 2024-2028
3.2 Readiness Plan
3.2.1 Training and Exercise Plan
3.3 Response Plan
3.3.1 Information-Sharing Plan
3.3.2 Resource Management Plan
3.3.3 Workforce Readiness / Resilience Plan
3.3.4 Medical Surge Support Plan
3.3.5 Patient Movement Plan
3.3.6 Allocation of Scarce Resources Plan
3.4 Continuity and Recovery Plan
3.4.1 Continuity of Operations Plan (COOP)
3.4.2 Cybersecurity Support Plan
3.4.3 Extended Downtime Support Plan
3.4.4 Recovery Plan
4. Exercise and Improve
4.1 Medical Response and Surge Exercise (MRSE)
4.2 Patient Movement Exercise
4.3 Federal Patient Movement Exercise
4.4 Cybersecurity Exercise
4.5 Non-Cyber Extended Downtime Exercise
4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement
4.7 Statewide Exercise
Other
X2A0T

## HCC Development
Readiness Plan – HCC Growth & Development
Activities listed below must support the administrative management and monitoring of the cooperative agreement.
Instructions and reminders:
Describe how your HCC(s) will develop as an organization, including how your HCC(s) will: 1) Manage and improve administrative and financial functions. 2) Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).
Please provide at least one activity for program administration, financial administration, and strategic communication.
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This must be the role title of the personnel responsible for the administration or management activity and can speak to the intended output.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Item Number | HCC Development Activity | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date
Example | Sub-recipient Monitoring and Management | In coordination with the Program Director, the HPP Finance team will perform site visits to each sub-recipient to audit finance and program activities in Budget Period 1. | Site visit report includes financial audit for each sub-recipient. | Finance Director | 2025-06-30
1 | HCC Administration | Create Strategic plan to address high priority threats and opportunities (conduct SWOT with members, prepare draft at Board retreat, share draft and final plan with members) | 2025-2027 Strategic Plan | Lynne Drawdy Info@centralfladisaster.org | 2025-06-30
| HCC Administration | Update traffic light/project plan monthly and share with Board and members | Board and members are kept informed of deliverables, projects | Lynne Drawdy Info@centralfladisaster.org
2 | Financial Administration | Provide monthly and quarterly financial reports to Recipient and Board of Directors | Financial Sustainability | Lynne Drawdy Info@centralfladisaster.org | 2025-06-30
3 | Financial Administration | Complete quarterly state audits and annual single federal audit | No findings or audit exceptions | Lynne Drawdy Info@centralfladisaster.org
4 | Strategic Communication | Recruit and maintain members (through state and regional meetings, quarterly drills) | Updated membership list | Lynne Drawdy Info@centralfladisaster.org | 2025-06-30
4 | Strategic Communication | Ongoing communications with members, including quarterly meetings, quarterly communications drills, sharing information of benefit to members (e.g., trainings, exercises, situational awareness) | Members are informed of important information | Lynne Drawdy Info@centralfladisaster.org | 2025-06-30
5 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
6 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
7 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
8 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
9 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
10 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
11 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
12 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
13 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
14 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
15 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
16 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
17 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
18 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
19 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
20 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
21 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
22 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
23 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
24 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
25 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
26 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
27 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
28 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
29 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
30 | Select One | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy]
End of Worksheet
Select One
HCC Administration
Financial Administration
Strategic Communication
X3A0T

## Establish Governance
Readiness Plan – Implementation Planning: Establish Governance
Activities listed below must support establishing governance in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | HCC Governance Document | Review and update governance document annually | Updated governance document | Lynne Drawdy Info@centralfladisaster.org | 2025-05-30 | Organizational development | Enhance and sustain HCCs
2 | Select one | Review and update governance document annually | Updated governance document | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
3 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
4 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
5 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
6 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
7 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
8 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
9 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
10 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
11 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
12 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
13 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
14 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
15 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
16 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
17 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
18 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
19 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
20 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
21 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
22 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
23 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
24 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
25 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
26 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
27 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
28 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
29 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
30 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
End of Worksheet
X4A0T

## Assess Readiness
Readiness Plan – Implementation Planning: Assess Readiness
Activities listed below must support assessing readiness in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Work Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | Hazard Vulnerability Assessment (HVA) | CFDMC will conduct an annual risk assessment with input and data from local, regional, state and federal partners. | Completed HVA | Lynne Drawdy; info@centralfladisaster.org | 2025-01-15 | Assessment and risk mitigation | Establish and act upon multi-year priorities
2 | Readiness Assessment | CFDMC will conduct an annual readiness assessment with input from partners and members | Completed Readiness Assessment | Lynne Drawdy; info@centralfladisaster.org | 2025-01-15 | Assessment and risk mitigation | Establish and act upon multi-year priorities
3 | Supply Chain Integrity Assessment | CFDMC will coordinate with hospitals, emergency management vendors and other partners to update a supply chain integrity assessment and mitigation strategy. | Completed Supply Chain Integrity Assessment | Lynne Drawdy; info@centralfladisaster.org | 2025-01-15 | Assessment and risk mitigation | Coordination
4 | Cybersecurity Assessment | CFDMC will work with the Recipient, members, all Florida health care coalitions and other subject matter experts to conduct a cybersecurity assessment. This assessment will assess use of cybersecurity practices, describe community impact of a potential cyber incident on communities most impacted by disasters, and identify mitigation strategies. | Completed Cybersecurity Assessment | Lynne Drawdy; info@centralfladisaster.org | 2025-06-30 | Assessment and risk mitigation | Establish and act upon multi-year priorities
5 | Extended Downtime Health Care Delivery Impact Assessment | Coalition will work with hospitals, emergency management and other partners to complete a regional non-cyber extended downtime health care delivery impact assessment, including impacted functions, community impact, and mitigation strategies. | Completed Extended Downtime Health Care Delivery Impact Assessment | Lynne Drawdy; info@centralfladisaster.org | 2025-06-30 | Assessment and risk mitigation | Establish and act upon multi-year priorities
6 | Workforce Assessment | CFDMC will collaborate with members, community partners, and additional health care readiness partners to conduct a workforce assessment. This assessment will identify: vulnerabilities, ability to provide specialty expertise and provide care to communities most impacted by disasters, training needs, workforce safety and health resources, community impact and mitigation strategies | Completed Workforce Assessment | Lynne Drawdy; info@centralfladisaster.org | 2027-06-30 | Health care workforce support | Continuity of health care service delivery
7 | Risk Assessment (RA) | CFDMC will coordinate with local, regional and state emergency management and other partners, incorporating input from all members, to complete an updated regional risk assessment. | Completed Risk Assessment | Lynne Drawdy; info@centralfladisaster.org | 2029-06-30 | Assessment and risk mitigation | Establish and act upon multi-year priorities
8 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
9 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
10 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
11 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
12 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
13 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
14 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
15 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
16 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
17 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
18 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
19 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
20 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
21 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
22 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
23 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
24 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
25 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
26 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
27 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
28 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
29 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
30 | Select one | [insert Work Plan Activity] | [insert Intended Output] | [insert Point of Contact] | [mm/dd/yyyy] | Select one | Select one
End of Worksheet
X5A0T

## Plan and Implement
Readiness Plan – Implementation Planning: Plan and Implement
Activities listed below must support planning and implementation in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | Readiness Plan | CFDMC will complete an annual readiness plan, based on the readiness assessment. The readiness plan will be shared with the CFDMC Board and members. | Readiness Plan is i[ to date | Lynne Drawdy; info@centralfladisaster.org | 2025-03-15 | Organizational development | Establish and act upon multi-year priorities
2 | Training and Exercise Plan | CFDMC coordinates with local, regional and state partners to develop an integrated IPPW. | Training and Exercise Plan is up to date (See T&E Plan tab) | Lynne Drawdy; info@centralfladisaster.org | 2025-03-15 | Training, exercise, and evaluation | Establish and act upon multi-year priorities
3 | Strategic Plan for FY 2024-2028 | CFDMC will participate in all strategic planning activities laid out by the Recipient in helping them formulate a state-wide Strategic Plan, including attendance at PAC meetings | A state-wide Strategic Plan, with input from all HCCs | Lynne Drawdy; info@centralfladisaster.org | 2025-06-15 | Organizational development | Establish and act upon multi-year priorities
4 | Response Plan | CFDMC will develop a response plan including information sharing, resource management and medical surge management. | Response Plan is up to date | Lynne Drawdy; info@centralfladisaster.org | 2025-06-15 |  | Establish and act upon multi-year priorities
5 | Continuity and Recovery Plan: Continuity of Operations Plan (COOP) | CFDMC will update its COOP plan | Continuity of Operations Plan is up to date | Lynne Drawdy; info@centralfladisaster.org | 2025-06-15 | Continuity and recovery | Continuity of health care service delivery
6 | Response Plan: Medical Surge Support Plan | CFDMC will review and update its response plan annexes (burn, trauma, pediatrics, infectious diseases, chemical, radiological, infectious diseases) | Response Plan Annexes are up to date | Lynne Drawdy; info@centralfladisaster.org | 2025-06-30 | Respond | Establish and act upon multi-year priorities
7 | Continuity and Recovery Plan: Cybersecurity Support Plan | CFDMC will partner with the regional cybersecurity initiative, using the results from the cybersecurity assessment, to identify and implement high-impact cybersecurity practices and a regional cybersecurity response plan. | Cybersecurity Support and Response Plan | Lynne Drawdy; info@centralfladisaster.org | 2026-06-30 | Continuity and recovery | Continuity of health care service delivery
8 | Continuity and Recovery Plan: Extended Downtime Support Plan | CFDMC will utilize the results from the Extended Downtime Health Care Delivery Impact Assessment to develop a plan to address identified gaps, including prevention and preparedness actions, and to address the management and mitigation of disruptions to clinical or operational activities from a downtime event impacting the region. | Extended Downtime Support Plan | Lynne Drawdy; info@centralfladisaster.org | 2026-06-30 | Continuity and recovery | Continuity of health care service delivery
9 | Continuity and Recovery Plan: Recovery Plan | CFDMC will update it's Recovery Plan to include integration with key partners, supporting the healthcare workforce, prioritizing critical infrastructure recovery, addressing anticipated recovery needs for the community, and engaging with and supporting community partners in recovery. | Recovery Plan is expanded and update to date | Lynne Drawdy; info@centralfladisaster.org | 2026-06-30 | Continuity and recovery | Continuity of health care service delivery
10 | Response Plan: Workforce Readiness / Resilience Plan | CFDMC will partner with members to develop a plan that addresses gaps identified in the workforce assessment, supports the healthcare workforce's access to resources, supports workforce safety and resilience, and engages the health care workforce in trainings and exercises.` | Workforce Readiness/Resilience Plan | Lynne Drawdy; info@centralfladisaster.org | 2027-06-30 | Health care workforce support | Continuity of health care service delivery
11 | Response Plan: Patient Movement Plan | CFDMC will partner with the Florida Committee on Trauma, the Trauma Preparedness Committee, and other community partners to develop a regional patient movement plan (MOCC). | Patient Movement Plan | Lynne Drawdy; info@centralfladisaster.org | 2028-06-30 | Specialty care planning and coordination | Coordination
12 | Response Plan: Allocation of Scarce Resources Plan | CFDMC will develop and maintain an Allocation of Scarce Resources Plan, using the Crisis Standards of Care plan developed by CFDMC and community partners. | Allocation of Scarce Resources Plan | Lynne Drawdy; info@centralfladisaster.org | 2028-06-30 | Resource management | Coordination
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
| Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
End of Worksheet
X6A0T

## Exercise and Improve
Readiness Plan – Implementation Planning: Exercise and Improve
Activities listed below must support exercises and improvement in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | Medical Response Surge Exercise (MRSE) | CFDMC will hold an annual MRSE during which hospitals and emergency management will surge according to the MRSE exercise requirements. | MRSE Tool | CFDMC and Exercise Planning Team | 2025-04-10 | Training, exercise, and evaluation | 4.1 Medical Response and Surge Exercise (MRSE)
2 | Patient Movement Exercise | CFDMC will conduct a Patient Movement Exercise upon completion of its Patient Movement Plan | Patient Movement Exercise AAR/IP | CFDMC and Exercise Planning Team | 2029-06-30 | Training, exercise, and evaluation | 4.2 Patient Movement Exercise
3 | Federal Patient Movement Exercise | CFDMC will work with the FCC Coordinators in Tampa and Miami to identify an opportunity to fully participate in the NDMS Exercise. | CFDMC participation in NDMS exercise | CFDMC and Exercise Planning Team | 2029-06-30 | Training, exercise, and evaluation | 4.3 Federal Patient Movement Exercise
4 | Cybersecurity Exercise | CFDMC will conduct a second Cybersecurity Exercise upon completion of its Cybersecurity Support Plan. An AAR will be developed and submitted | Cybersecurity Exercise AAR/IP | CFDMC and Exercise Planning Team | 2026-04-30 | Training, exercise, and evaluation | 4.4 Cybersecurity Exercise
5 | Non-Cyber Extended Downtime Exercise | CFDMC will conduct a Non-Cyber Extended Downtime Exercise upon completion of its Extended Downtime Support Plan | Non-Cyber Extended Downtime Exercise AAR/IP | CFDMC and Exercise Planning Team | 2028-05-30 | Training, exercise, and evaluation | 4.5 Non-Cyber Extended Downtime Exercise
6 | Regional Exercises | CFDMC will conduct exercises that address regional risk, priorities or gaps as identified in previous exercises. These are identified in the T&E Plan. | Regional Exercises AAR/IP (annually) | CFDMC and Exercise Planning Team | 2029-05-30 | Training, exercise, and evaluation | 4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement
7 | Statewide Exercise | In collaboration with the Recipient, CFDMC will participate in a statewide exercise during which it will collaborate with health care readiness partners including Public Health, State Emergency Management, Other HCCs, and Additional Health Care Readiness Partners | Statewide Exercise AAR/IP | CFDMC, FDOH and Exercise Planning Team | 2028-05-30 | Training, exercise, and evaluation | 4.7 Statewide Exercise
8 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
9 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
10 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
11 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
12 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
13 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
14 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
15 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
16 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
17 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
18 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
19 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
20 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
21 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
22 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
23 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
24 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
25 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
26 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
27 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
28 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
29 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
30 | Select one | [insert Readiness Plan Activity] | [insert Intended Output] | [insert Activity Point of Contact] | [mm/dd/yyyy] | Select one | Select one
End of Worksheet
X7A0T

## T&E Plan Instructions
Hospital Preparedness Program (HPP) HCC T&E Plan Template Overview
Purpose | The Administration for Strategic Preparedness and Response (ASPR)’s OHCR developed a template for the T&E Plan to support you and your HCCs with completing activity requirements for the T&E Plan. Please refer to the FY 2024–2028 HPP NOFO for more information.
NOFO Instructions | Template content: The T&E Plan template contains a detailed table to organize a timeline of all planned and projected trainings and exercises for the FY 2024–2028 period of performance, beginning on July 1, 2024, and ending on June 30, 2029. An example is provided. Submission deadline and updates: The T&E Plan is due by March 31, 2025. You and your HCC(s) must provide information for trainings and exercises for all five BPs. You and your HCC(s) must make updates and submit a revised T&E Plan each BP from BP2–BP5. Please provide the date of your last update in the footer of the template. • Identify the type of exercise, which can be one of the following: • Seminar. • Workshop. • Tabletop exercise. • Drill. • Functional exercise. • Full-scale exercise. • Address communities most impacted by disasters (p. 14 of the HPP NOFO). • Include engagement with health care readiness partners, as appropriate (p. 13-15 of the HPP NOFO). • Describe how you and your HCC(s) will engage the health care workforce in trainings and exercises (p. 30 of the HPP NOFO). • Include, as appropriate, any trainings and exercises in the example list of topics (p. 89 of the HPP NOFO). Please note the following funding policies and limitations (p. 51 of the HPP NOFO): • You may not use funds to support standalone, single-facility exercises. • You may not spend HPP funds on training courses, exercises, and planning resources when similar offerings are available at no cost.
Your T&E Plan must, at a minimum, include the following required trainings and exercises:
Training/Exercise | Submission Instructions and Timeline
National Incident Management System (NIMS) training | Throughout the five-year period of performance.
Medical Response and Surge Exercise (MRSE) | Complete the exercise and submit the MRSE Exercise Reporting Tool by June 30 of each BP.
Patient Movement Exercise | Complete once, within one year of submitting the Patient Movement Plan.
Federal Patient Movement Exercise | If applicable, complete once every three years, or as required by other cooperative agreements/programs.
Cybersecurity Exercise | Complete once by June 30, 2027 (BP3).
Non-Cyber Extended Downtime Exercise | Complete once between BP3–BP5.
Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Complete once in the five-year period of performance.
Statewide Exercise | Complete once in the five-year period of performance.
If you decide to make this the Recipient T&E Plan template, recipients with large numbers of HCCs (e.g., CA) may have an issue with listing every HCC's annual MRSE.
In those situations, we can add a caveat to only list a MRSE in their plan if they have a significant role.
End of Worksheet
X8A0T

## T&E Plan
HPP HCC T&E Plan
HCC name: | CFDMC
Date of last update: | 2025-03-14
BP1
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
2025-08-01 | Patient Movement Exercise | Full-scale exercise | Major flooding | Hospitals, LTC, EMS, EM, & HCCs | State MOCC, OEM, & DOT | FEMA Regional Response Plans | Joe Smith joesmith@gmail.com
Monthly | COOP Training | Virtual | Continuity of Operations | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
Monthly | CEMP Training | Virtual | Comprehensive Emergency Management Plans | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
2024-07-29 | 0305-All Hazards Incident Management Team | In Person | Incident Management | Regional Incident Management Team members; regional medical assistance team members; emergency managers; county health departments | Emergency management |  | Lynne Drawdy; info@centralfladisaster.org
2024-08-22 | MGT-340 - Crisis Leadership Training | In Person | High Consequence Infectious Disease | Hospitals, Emergency Management, Clinicians | TEEX |  | Lynne Drawdy; info@centralfladisaster.org
2024-10-11 | Hospital Incident Command System (HICS) | In Person | Incident Management | Hospital leadership |  |  | Lynne Drawdy; info@centralfladisaster.org
2024-12-03 | Certified Health Safety Professional | In Person | Incident Management | Hospital emergency preparedness staff |  |  | Lynne Drawdy; info@centralfladisaster.org
2025-02-10 | L950-Incident Commander | In Person | Incident Management | Regional Incident Management Team members; regional medical assistance team members; emergency managers | Emergency management |  | Lynne Drawdy; info@centralfladisaster.org
2025-03-11 | L965-Resource Unit Leader | In Person | Incident Management | Regional Incident Management Team members; regional medical assistance team members; emergency managers | Emergency management |  | Lynne Drawdy; info@centralfladisaster.org
2024-09-20 | Operation Protect & Secure | Functional | Active Shooter | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
2024-10-30 | Cyber TTX | Tabletop | Cyber Security & Response | Hospitals, Emergency management, regional leaders | CISA |  | Lynne Drawdy; info@centralfladisaster.org
2024-12-03 | A Glass of Mutual Aid | Functional | Test mutual aid agreements | Healthcare organizations | Emergency management | Facility mutual aid agreements/vendor contracts | Lynne Drawdy; info@centralfladisaster.org
2025-02-05 | Great Tornado Drill | Functional | Test shelter in place plans | All Members | NWS, FDEM, emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
2025-02-05 | 15 till 50 | Full-scale exercise | Test medical surge | Hospital (Holmes) | FDOH, 15 till 50 Consultant | Facility response plan | Lynne Drawdy; info@centralfladisaster.org
2025-02-27 | FIDTN | Full-scale exercise | Test ability to identify, isolate, inform, treat and transport high consequence infectious disease patient | Hospital (AdventHealth Waterman) | FDOH, FIDTN Team | Regional and hospital infectious disease plans | Lynne Drawdy; info@centralfladisaster.org
2025-04-10 | Trouble in the Air | Full-scale exercise | MRSE | Hospitals, Emergency Management | 100 plus partners | Coalition and hospital response plans | Lynne Drawdy; info@centralfladisaster.org
2025-05-21 | Operation Generate Confidence | Functional | Generator drill | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
BP2
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact | Column1
Monthly | COOP Training | Virtual | Continuity of Operations | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
Monthly | CEMP Training | Virtual | Comprehensive Emergency Management Plans | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
Quarterly | Incident Management Team Command Staff / team trainings | In Person | Incident Management | Regional Incident Management Team members; regional medical assistance team members; emergency managers; county health departments | Emergency management |  | Lynne Drawdy; info@centralfladisaster.org
Annual (September) | Operation Protect & Secure | Functional | Active Shooter | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (December) | A Glass of Mutual Aid | Functional | Test mutual aid agreements | Healthcare organizations | Emergency management | Facility MOAs/vendor contracts | Lynne Drawdy; info@centralfladisaster.org
Annual (February) | Great Tornado Drill | Functional | Test shelter in place plans | All Members | NWS, FDEM, emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (April) | Trouble in the Air | Full-scale exercise | MRSE | Hospitals, Emergency Management | 100 plus partners | Coalition and facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (May) | Operation Generate Confidence | Functional | Generator drill | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
TBD | Family Reunification Exercises | Tabletop | Address high priority HVA gap | Hospitals, Emergency Management, Schools | Red Cross | FRC/FAC plans | Lynne Drawdy; info@centralfladisaster.org
2026-04-01 | Cybersecurity Exercise | TTX | Continuity of Operations | Hospitals, emergency management, other coalition members | CISA | Cybersecurity plans | Lynne Drawdy; info@centralfladisaster.org
BP3
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
Monthly | COOP Training | Virtual | Continuity of Operations | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
Monthly | CEMP Training | Virtual | Comprehensive Emergency Management Plans | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
Quarterly | Incident Management Team Command Staff / team trainings | In Person | Incident Management | Regional Incident Management Team members; regional medical assistance team members; emergency managers; county health departments | Emergency management |  | Lynne Drawdy; info@centralfladisaster.org
Annual | Hospital Incident Command System (HICS) | In Person | Incident Management | Hospital leadership |  |  | Lynne Drawdy; info@centralfladisaster.org
Annual | Certified Health Emergency Professional (CHEP) | In Person | Incident Management | Hospital emergency preparedness staff |  |  | Lynne Drawdy; info@centralfladisaster.org
Annual (September) | Operation Protect & Secure | Functional | Active Shooter | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (December) | A Glass of Mutual Aid | Functional | Test mutual aid agreements | Healthcare organizations | Emergency management | Facility MOAs/vendor contracts | Lynne Drawdy; info@centralfladisaster.org
Annual (February) | Great Tornado Drill | Functional | Test shelter in place plans | All Members | NWS, FDEM, emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (April) | Trouble in the Air | Full-scale exercise | MRSE | Hospitals, Emergency Management | 100 plus partners | Coalition and facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (May) | Operation Generate Confidence | Functional | Generator drill | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
Federal Patient Movement Exercise | Full-Scale | Medical Surge | Patient Movement | Hospitals, EMS, emergency management, health departments, FCC, VA | FCC/VA | Coalition and facility response plans | Lynne Drawdy; info@centralfladisaster.org
BP4
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
Monthly | COOP Training | Virtual | Continuity of Operations | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
Monthly | CEMP Training | Virtual | Comprehensive Emergency Management Plans | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
Quarterly | Incident Management Team Command Staff / team trainings | In Person | Incident Management | Regional Incident Management Team members; regional medical assistance team members; emergency managers; county health departments | Emergency management |  | Lynne Drawdy; info@centralfladisaster.org
Annual | Hospital Incident Command System (HICS) | In Person | Incident Management | Hospital leadership |  |  | Lynne Drawdy; info@centralfladisaster.org
Annual | Certified Health Emergency Professional (CHEP) | In Person | Incident Management | Hospital emergency preparedness staff |  |  | Lynne Drawdy; info@centralfladisaster.org
Annual (September) | Operation Protect & Secure | Functional | Active Shooter | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (December) | A Glass of Mutual Aid | Functional | Test mutual aid agreements | Healthcare organizations | Emergency management | Facility MOAs/Vendor contracts | Lynne Drawdy; info@centralfladisaster.org
Annual (February) | Great Tornado Drill | Functional | Test shelter in place plans | All Members | NWS, FDEM, emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (April) | Trouble in the Air | Full-scale exercise | MRSE | Hospitals, Emergency Management | 100 plus partners | Coalition and facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (May) | Operation Generate Confidence | Functional | Generator drill | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
2028-03-01 | Non-Cyber Extended Downtime Exercise | TTX | Continuity of Operations/Business | Hospitals, Emergency Management, EMS, Health Departments, other healthcare entities | FDOH | State and regional Extended Downtime Support Plan | Lynne Drawdy; info@centralfladisaster.org
2028-05-01 | Statewide Exercise | TTX | TBD | TBD | FDOH | TBD | Lynne Drawdy; info@centralfladisaster.org
BP5
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
Monthly | COOP Training | Virtual | Continuity of Operations | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
Monthly | CEMP Training | Virtual | Comprehensive Emergency Management Plans | All Members | Statewide partnership among healthcare coalitions | BOLDplanning platform | Lynne Drawdy; info@centralfladisaster.org
Quarterly | Incident Management Team Command Staff / team trainings | In Person | Incident Management | Regional Incident Management Team members; regional medical assistance team members; emergency managers; county health departments | Emergency management |  | Lynne Drawdy; info@centralfladisaster.org
Annual | Hospital Incident Command System (HICS) | In Person | Incident Management | Hospital leadership |  |  | Lynne Drawdy; info@centralfladisaster.org
Annual | Certified Health Emergency Professional (CHEP) | In Person | Incident Management | Hospital emergency preparedness staff |  |  | Lynne Drawdy; info@centralfladisaster.org
Annual (September) | Operation Protect & Secure | Functional | Active Shooter | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (December) | A Glass of Mutual Aid | Functional | Test mutual aid agreements | Healthcare organizations | Emergency management | Facility MOAs/vendor contracts | Lynne Drawdy; info@centralfladisaster.org
Annual (February) | Great Tornado Drill | Functional | Test shelter in place plans | All Members | NWS, FDEM, emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (April) | Trouble in the Air | Full-scale exercise | MRSE | Hospitals, Emergency Management | 100 plus partners | Coalition and facility response plans | Lynne Drawdy; info@centralfladisaster.org
Annual (May) | Operation Generate Confidence | Functional | Generator drill | All Members | Emergency management | Facility response plans | Lynne Drawdy; info@centralfladisaster.org
2029-03-01 | Patient Movement Exercise | Functional | Medical Surge and Patient Movement | Hospitals, EMS, Emergency Management, health departments | FDOH | Regional and state patient movement plans | Lynne Drawdy; info@centralfladisaster.org
End of Worksheet
X9A0T

## Instructions (hidden)
ASPR HPP FY2019-2023 HCC Budget: Instructions
1) Proceed to the worksheet tab for each category that funding is requested
2) For each line item, fully complete the data fields for the entire row
3) For cells with a dropdown menu, please select the most appropiate response; do not enter custom text
4) For cells requesting a custom text, be clear and concise to ensure text limits are not exceeded
5) When entering detailed justification statements, be clear and concise to ensure text limits are not exceeded.
6) All dollar amounts to be funded by the program must be fully accounted for; this includes allocation breakdowns between capabilities as well as when cost share is being applied between programs (i.e. HPP vs. PHEP)
7) All line items must be associated with an appropiate HPP activity or multiple activities; failure to identify HPP activities may result in budget restrictions
8) All HPP activities identified in the HCC Budget must be accounted for in the HCC Work Plan; failure to account for HPP activities in the HCC Work Plan may result in budget restrictions

## Sheet1 (hidden)
0. Administrative Oversight
0.1 Program Administration
0.2 Financial Administration
0.3 Sub-recipient Monitoring and Management
0.4 Program Reporting
0.5 Performance Evaluation
1. Establish governance
1.1 HCC Governance Document
1.2 Jurisdiction Information
2. Assess readiness
2.1 Risk Assessment (RA)
2.2 Hazard Vulnerability Assessment (HVA)
2.3 Readiness Assessment
2.4 Supply Chain Integrity Assessment
2.5 Workforce Assessment
2.6 Cybersecurity Assessment
2.7 Extended Downtime Health Care Delivery Impact Assessment
3. Plan and implement
3.1 Strategic Plan for FY 2024-2028
3.2 Readiness Plan
3.2.1 Training and Exercise Plan
3.3 Response Plan
3.3.1 Information-Sharing Plan
3.3.2 Resource Management Plan
3.3.3 Workforce Readiness / Resilience Plan
3.3.4 Medical Surge Support Plan
3.3.5 Patient Movement Plan
3.3.6 Allocation of Scarce Resources Plan
3.4 Continuity and Recovery Plan
3.4.1 Continuity of Operations Plan (COOP)
3.4.2 Cybersecurity Support Plan
3.4.3 Extended Downtime Support Plan
3.4.4 Recovery Plan
4. Exercise and Improve
4.1 Medical Response and Surge Exercise (MRSE)
4.2 Patient Movement Exercise
4.3 Federal Patient Movement Exercise
4.4 Cybersecurity Exercise
4.5 Non-Cyber Extended Downtime Exercise
4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement
4.7 Statewide Exercise

## Data Validation (hidden)
Data Validation
Administrative Oversight | 1. Establish Governance |  |  | 2. Assess Readiness |  |  | 3. Plan and Implement |  |  | 4. Exercise and Improve |  |  | Budget - Personnel |  | Budget - Personnel |  | Budget - Travel | Budget - Contractual |  | Budget - Indirect Costs | Budget - Match
Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select One | Select one | 0% | 0% | Select one | Select one | Select one | (Yes/No) | Select one
Program Administration | HCC Governance Document | Assessment and risk mitigation | Establish and act upon multi-year priorities | Risk Assessment (RA) | Assessment and risk mitigation | Establish and act upon multi-year priorities | Strategic Plan for FY 2024-2028 | Assessment and risk mitigation | Establish and act upon multi-year priorities | Medical Response Surge Exercise (MRSE) | Assessment and risk mitigation | Establish and act upon multi-year priorities | 0. Administrative Oversight | Recipient | 1% | 1% | In state | Commercial | Monthly | Yes | Cash
Financial Administration | Jurisdiction Information | Information sharing | Enhance and sustain HCCs | Hazard Vulnerability Assessment (HVA) | Information sharing | Enhance and sustain HCCs | Readiness Plan | Information sharing | Enhance and sustain HCCs | Patient Movement Exercise | Information sharing | Enhance and sustain HCCs | 0.1 Program Administration | Health care coalition | 2% | 2% | Out of state | Health care coalition | Quarterly | No | In-kind contributions
Sub-recipient Monitoring and Management |  | Specialty care planning and coordination | Coordination | Readiness Assessment | Specialty care planning and coordination | Coordination | Training and Exercise Plan | Specialty care planning and coordination | Coordination | Federal Patient Movement Exercise | Specialty care planning and coordination | Coordination | 0.2 Financial Administration | Multiple | 3% | 3% |  | Other public entity | Semi-Annual
Program Reporting |  | Respond | Continuity of health care service delivery | Supply Chain Integrity Assessment | Respond | Continuity of health care service delivery | Response Plan: Information-Sharing Plan | Respond | Continuity of health care service delivery | Cybersecurity Exercise | Respond | Continuity of health care service delivery | 0.3 Sub-recipient Monitoring and Management | Other | 4% | 4% |  | State or local hospital association | Annual
Performance Evaluation |  | Health care workforce support |  | Workforce Assessment | Health care workforce support |  | Response Plan: Resource Management Plan | Health care workforce support |  | Non-Cyber Extended Downtime Exercise | Health care workforce support |  | 0.4 Program Reporting |  | 5% | 5% |  | Business support services
|  | Resource management |  | Cybersecurity Assessment | Resource management |  | Response Plan: Workforce Readiness / Resilience Plan | Resource management |  | Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Resource management |  | 0.5 Performance Evaluation |  | 6% | 6% |  | Information Technology (IT) consulting services
|  | Training, exercise, and evaluation |  | Extended Downtime Health Care Delivery Impact Assessment | Training, exercise, and evaluation |  | Response Plan: Medical Surge Support Plan | Training, exercise, and evaluation |  | Statewide Exercise | Training, exercise, and evaluation |  | 1. Establish governance |  | 7% | 7% |  | Private laboratory (non-university affiliated)
|  | Continuity and recovery |  |  | Continuity and recovery |  | Response Plan: Patient Movement Plan | Continuity and recovery |  |  | Continuity and recovery |  | 1.1 HCC Governance Document |  | 8% | 8% |  | Security services
|  | Organizational development |  |  | Organizational development |  | Response Plan: Allocation of Scarce Resources Plan | Organizational development |  |  | Organizational development |  | 1.2 Jurisdiction Information |  | 9% | 9% |  | Temporary staff agency
[7 empty] | Continuity and Recovery Plan: Continuity of Operations Plan (COOP) | [5 empty] | 2. Assess readiness |  | 10% | 10% |  | Inter-agency department/division
[7 empty] | Continuity and Recovery Plan: Cybersecurity Support Plan | [5 empty] | 2.1 Risk Assessment (RA) |  | 11% | 11% |  | Local public health department / agency
[7 empty] | Continuity and Recovery Plan: Extended Downtime Support Plan | [5 empty] | 2.2 Hazard Vulnerability Assessment (HVA) |  | 12% | 12% |  | National or federal government agency
[7 empty] | Continuity and Recovery Plan: Recovery Plan | [5 empty] | 2.3 Readiness Assessment |  | 13% | 13% |  | Public health laboratory
[13 empty] | 2.4 Supply Chain Integrity Assessment |  | 14% | 14% |  | Tribal entities / government
[13 empty] | 2.5 Workforce Assessment |  | 15% | 15% |  | Other local government agencies
[13 empty] | 2.6 Cybersecurity Assessment |  | 16% | 16% |  | Other state government agencies
[13 empty] | 2.7 Extended Downtime Health Care Delivery Impact Assessment |  | 17% | 17% |  | Police, fire, HAZMAT, or emergency medical services
[13 empty] | 3. Plan and implement |  | 18% | 18% |  | Local schools, educational institutions, and school boards
[13 empty] | 3.1 Strategic Plan for FY 2024-2028 |  | 19% | 19% |  | Health care facilities and networks - Inpatient
[13 empty] | 3.2 Readiness Plan |  | 20% | 20% |  | Poison Control Center
[13 empty] | 3.2.1 Training and Exercise Plan |  | 21% | 21% |  | Health care facilities and networks – Outpatient
[13 empty] | 3.3 Response Plan |  | 22% | 22% |  | University (both public and private institutions)
[13 empty] | 3.3.1 Information-Sharing Plan |  | 23% | 23% |  | Faith-based organization
[13 empty] | 3.3.2 Resource Management Plan |  | 24% | 24% |  | Private non-profit organization
[13 empty] | 3.3.3 Workforce Readiness / Resilience Plan |  | 25% | 25% |  | Contracts – Other
[13 empty] | 3.3.4 Medical Surge Support Plan |  | 26% | 26%
[13 empty] | 3.3.5 Patient Movement Plan |  | 27% | 27%
[13 empty] | 3.3.6 Allocation of Scarce Resources Plan |  | 28% | 28%
[13 empty] | 3.4 Continuity and Recovery Plan |  | 29% | 29%
[13 empty] | 3.4.1 Continuity of Operations Plan (COOP) |  | 30% | 30%
[13 empty] | 3.4.2 Cybersecurity Support Plan |  | 31% | 31%
[13 empty] | 3.4.3 Extended Downtime Support Plan |  | 32% | 32%
[13 empty] | 3.4.4 Recovery Plan |  | 33% | 33%
[13 empty] | 4. Exercise and Improve |  | 34% | 34%
[13 empty] | 4.1 Medical Response and Surge Exercise (MRSE) |  | 35% | 35%
[13 empty] | 4.2 Patient Movement Exercise |  | 36% | 36%
[13 empty] | 4.3 Federal Patient Movement Exercise |  | 37% | 37%
[13 empty] | 4.4 Cybersecurity Exercise |  | 38% | 38%
[13 empty] | 4.5 Non-Cyber Extended Downtime Exercise |  | 39% | 39%
[13 empty] | 4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement |  | 40% | 40%
[13 empty] | 4.7 Statewide Exercise |  | 41% | 41%
[15 empty] | 42% | 42%
[15 empty] | 43% | 43%
[15 empty] | 44% | 44%
[15 empty] | 45% | 45%
[15 empty] | 46% | 46%
[15 empty] | 47% | 47%
[15 empty] | 48% | 48%
[15 empty] | 49% | 49%
[15 empty] | 50% | 50%
[15 empty] | 51% | 51%
[15 empty] | 52% | 52%
[15 empty] | 53% | 53%
[15 empty] | 54% | 54%
[15 empty] | 55% | 55%
[15 empty] | 56% | 56%
[15 empty] | 57% | 57%
[15 empty] | 58% | 58%
[15 empty] | 59% | 59%
[15 empty] | 60% | 60%
[15 empty] | 61% | 61%
[15 empty] | 62% | 62%
[15 empty] | 63% | 63%
[15 empty] | 64% | 64%
[15 empty] | 65% | 65%
[15 empty] | 66% | 66%
[15 empty] | 67% | 67%
[15 empty] | 68% | 68%
[15 empty] | 69% | 69%
[15 empty] | 70% | 70%
[15 empty] | 71% | 71%
[15 empty] | 72% | 72%
[15 empty] | 73% | 73%
[15 empty] | 74% | 74%
[15 empty] | 75% | 75%
[15 empty] | 76% | 76%
[15 empty] | 77% | 77%
[15 empty] | 78% | 78%
[15 empty] | 79% | 79%
[15 empty] | 80% | 80%
[15 empty] | 81% | 81%
[15 empty] | 82% | 82%
[15 empty] | 83% | 83%
[15 empty] | 84% | 84%
[15 empty] | 85% | 85%
[15 empty] | 86% | 86%
[15 empty] | 87% | 87%
[15 empty] | 88% | 88%
[15 empty] | 89% | 89%
[15 empty] | 90% | 90%
[15 empty] | 91% | 91%
[15 empty] | 92% | 92%
[15 empty] | 93% | 93%
[15 empty] | 94% | 94%
[15 empty] | 95% | 95%
[15 empty] | 96% | 96%
[15 empty] | 97% | 97%
[15 empty] | 98% | 98%
[15 empty] | 99% | 99%
[15 empty] | 100% | 100%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Tran-Kiem, Jenn @Hitchcock, Katherine @Drobac, Camila All the Data Validation options on respective tabs I relocated here to reduce user error. I suggest hiding this sheet in final version.